## Sheet1
Development / Project | Business driver / Justification | Sponsor / Requestor | Project Lead | Priority 1-3 (1=High) | Target Completion date | Status | RAG | Comments / updates
Migrate to Cloud Telephony Service - approx 1550 handsets | Current system goes end of support in mid Oct 2016 | CCG | SC | 1 | 2016-10-31 | In Progress |  | 3/6/16 - Finances approved. GM SS told to progress. 17/5/16 - Determining costs to migrate to due incompatibility issues with 700 handsets 18/6/2016 Comms distributed to Practices
Interface Stockport Partner telephony systems over CoIN | Calls between NHS & Local Gov would be Free of Charge | CCG | SC | 2 | 2016-12-01 | Future Dev. |  | 17/5/16 - implementation costs TBC.
Deploy Cloud Telephony Service to all Practices. | Calls between from Practices to other users on the Cloud Telephony Service are FoC. Would allow greater mobility for staff who can use handsets at relevant sites. | CCG | SC | 2 | 2017-03-01 | Future Dev.
EMIS GP migrations | Standardise Primary Care systems across Locality | Stockport Together | SC | 1 | 2016-12-01 | In Progress |  | 6/6/16 - 7 Practices to do - 4 scheduled for completion by end of Sept 2016. Further funding needed to complete the remaining sites. 17/5/16 - 8 Practices to do. £142K investment required.
Implementation of Electronic Prescribing Service |  | NHS E. | SC | 1 |  | In Progress |  | 17/5/16 -
SHCR - add additonal data feeds from relevant Source systems | Ensure all relevant source systems are replicating relavent data to SHCR | Stockport Together | JO | 1 |  |  |  | 17/5/16 - DSA needs to signed off. Source systems to be added include Stockport Community (EMIS), Mental Health (Paris); Access to 111, NWAS...
SHCR - expand access to relavent H&SC staff | Ensure all relevant source system data feeds are in place and relevant Care Practitioners have access to it | Stockport Together | JO | 1 |  |  |  | 17/5/16 - DSA needs to signed off. Source systems to be added include Stockport Community (EMIS), Mental Health (Paris); Access to 111, NWAS...
SHCR - Migrate to GM Care Centric instance | Will allow data to be shared across 4 GM Localties / 6 CCG's. | Stockport Together | JO | 1 |  |  |  | 18/6/2016 Meeting attended and Dan Alexander needs to source resource for GM Instance set up
SHCR - upgrade to Care Centric from V2 to V3 | Delivers increased functionality, including integrated care paths / care plans, real-time data uploads from source systems and patient access to H&S record | Stockport Together | JO | 1 |  |  |  | 6/6/16 - Met with Graphnet to run through migraiton costs. Awaiting revised quote.
Develop business case for Docman Vault (Cloud version of Docman) | Facilitate remote access to Docman documents when not at the Practice. | CCG | SC | 1 | 2016-07-01 | In Progress
Implement Docman Vault | Facilitate remote access to Docman docuements when not at the Practice. | Primary Care | TBC | 1 | 2016-12-01 | Future Dev.
Implement Resource Domain | to allow H&S users to access relevant systems and data from any PC, at any H&S location in the Locality (Mobile Working) | Stockport Together | SC | 1
GM CoIN migrations | Standardise on single GM wide network | CCG / GM | SC | 1
Migrate to GM Active Directory | Standardise on single GM wide AD, to facilitate mobile working | CCG / GM | SC | 2 |  |  |  | 18/6/16 Comms sent out to all CCG users JO
Develop Safeguarding alerting for Children & Vulnerable adults | Reduce clinical risk | Dr Hewitt | JO | 2 |  |  |  | 14/6/16 Met with Andria Walton Safeguarding Lead
Docman annotation of clinical letters at GP practices to send back electronically to FT | Reduce clinical risk and improve communication times and reduce postage costs at practices | Adam Fith Alan Gilman Simon Woodworth | JO | 2 |  |  |  | 15/6/16 Meeting arranged with Docman GP's and FT 22/6/16
Deliver relevant technologies to support MDTs and Neighbourhood working | Key to the success of Stockport Together |  | TBC | 1 |  |  |  | 17/5/16 - need to meet with Snr managers to determine workflow & how ICT can support it. 18/6/16 Workshop attended by JO 17/6/16 for input to Business Cases
Pilot telemedicine solutions |  |  | TBC | 2
Engage with GM H&SC Partnership re GM Devolution | Ensure Stockport is represented at GM level and align Locality developments with GM aspirations | CCG | SC | 2 |  |  |  | 17/5/16 - debate as to GM IDCR standards and systems
Produce Locality / GM Digital Maturity Roadmap | funding stream for other IM&T related developments | NHS E. | SC | 1 |  |  |  | 17/5/16 - GM DMR is currently being prepared by WWL CCG
Setup IM&T Programme on relevant system | Improved management of IM&T projects and increased visability | AD IM&T | SC | 1 |  |  |  | 17/5/16 -looking to use CCG Business Management System (BMS).
Deploy NHS.net accts for Care Homes | Secure communication between Health/Social Care from the private sector Care Homes |  | AJ | 2 |  |  |  | AJ meeting arranged with LL for 22/06 to looking at creating policy templates for care homes as part of IG toolkit compliance
Access to Health & Social Care systems for Care Professionals working from Care Homes | Improved heath and care outcomes | Dr R Patel | AJ | 1 |  |  |  | Email from AJ 18/6/16 to SC re requirements
Diabetes in the Community | Initial meeting scheduled | Dr A Gilman | JO | 3 |  |  |  | Meeting requested with Peter Marks and Alan Gilman schedued for 23/6/16
Intermediate Care Homes SHCR and or Emis Viewer | Currently paper based and no electronic records available | Dr A Gilman | JO | 2
CHC Paperless Department/Service | To reduce costs and enable electronic access to records | SC | JO | 3 |  |  |  | JO Spoken to Donald Blackstock at SMBC if it would be possible to use EDRMS for storage and retrieval of diocs. EDRMS being replaced as not fit for purpose and unstable but could be an opportunity for CHC once new system procured
Emis Dementia Protocol | Standardise and improve Dementia protocol leading to improved health and care outcomes | Dr A Gilman and Nicole Alkemade | JO | 1 |  |  |  | Needs to be ready to roll out at GP Masterclass in September 18/6/2016 Template reviewed by Nicole Alkemede and Alan Gilman. Review scheduled with Dentia specialist nurse
Health Protection Team | Improved heath and care outcomes | Eleanor Bannister | JO | 2 |  |  |  | Template designed ready for Graphnet quote for inclusion in SHCR
Data Sharing Agreements | Sharing of information improving health and care | Stockport Together | JO/LL | 1 |  |  |  | I have included this as there are a raft of Tier 2 agreements required following the DSA Tier 1 once agreed with LMC 18/6/16 LL advised Tier 1 back weith LMC and changes are expected to be reviewed by BMA and sent back imminently to LL
Business Continuity Plan | GPSoC compliance | Dr A Gilman | JO | 3 |  |  |  | GPSoC requires all practices to have a BCP. Template to be built.
GP Practice Audits | GPSoC compliance | Dr A Gilman | JO | 2 |  |  |  | Audit template completed with requests from 2 practices to be carried out. GMSBS currently audit practices but not for all required under GPSoC
Optometry Pilot | Sharing of information improving health and care | Matthew Williamson | JO | 3 |  |  |  | Access to SHCR. 07/06/16 Second draft of current state process map with Roachan Patel for review.
Community Pharmacy Pilot | Sharing of information improving health and care | Peter Marks | JO | 2 |  |  |  | Access to SHCR/EPAC
Standardising Templates and Protocols within Emis | To reduce costs and enable Integrated working | Dr A Gilman | JO | 3 |  |  |  | Business Case to be drafted with A Gilman
Notifications to NWAS and NHS111 re EPAC | NHS 111 and NWAS notifications | S Woodworth | JO | 2 |  |  |  | Meeting arranged with NHS 111 and SW
Mastercall Access to SHCR through Adastra to include FT Portal | Sharing of information improving health and care | PRG and John OMalley |  | 1 |  |  |  | 18/6/2016 Once access is possible then Mastercall to advise of Go Live date
Intermediate Care Bed System | Sharing of information improving health and care | Denise Britch | JO | 2 |  |  |  | 18/6/2016 Meeting attended with IC and JO to discuss requirements. This is also a requirement for Stockport Together
FT Portal interface through SHCR failing | Sharing of information improving health and care | JO | JO | 1 |  |  |  | 17/6/2016 FT Portal now working for GP Practices through SSO change of group policies instigated by AJ and now fixed
System Admin knowledge transfer | Sharing of information improving health and care | JO | AJ | 1 |  |  |  | 17/6/16 Sys admin lacking basic knowledge in sysadmin AJ giving tutorial sessions weekly for 2 hours. Starting from a very low level of understanding
EPAC Task and Finish Group | Sharing of information improving health and care | Dave Waterman | JO | 1 |  |  |  | 15/6/16 Request from Dave Waterman to reinstate Project Board as a Task and Finish Group for EPAC due to low usage
Wireless networking of boardroom projector | Ease of use | SC | AJ | 3 | 2016-06-01 | In progress |  | Awaiting GM SS to allocate fixed IP address
SHCR Tiered Access | Security, manageability and better IG compliance | JO | AJ | 2 | 2016-07-01 | In progress |  | SHCR document and systems permissions are currently being documented and reviewed with a view to standardising the current 47 user groups down to 8