## Slide 1: Providing NHS Services
Greater Manchester Primary School
MMR Plan
August 2023 to February 2024

## Slide 2: Overview of GM Cohort & Schools for MMR
Approx 990 Primary Schools across 10 boroughs with total cohort of approx 149,000
Children requiring 2 doses: 17,690
Children requiring 1 dose: 11,280
First and Second only doses to be offered in Autumn, second doses following firsts given in Autumn to be delivered in Jan/ Feb
Total number of doses offered will be: 46,660

## Slide 3: MMR Consent
Paper consent / E-consent/ offer to 100% of the full MMR unvaccinated cohort (those with zero or just one vaccine) from 04th September 2023.
Targeting schools with 30%+ unvaccinated first, then 15%+, then offer to all remaining GM schools.
Phone call consents with those cohorts in schools with under 30% vaccinated from mid-August (access to CHIS data permitting)
The offer will fall into the flu schedules as closely as we can match on consideration of numbers and pace of programme.
Data to be triaged against health care records to ensure accuracy of immunisation status and reduce the risk of incidents.

## Slide 4
3. Comms to Schools and Parents/Guardians
4. Schools booked in/ confirmed by team from 4th September
5. School sessions to commence by 11th September latest (Higher unvaccinated cohort schools taking priority)
6. School Sessions will combine offer of 1st MMR vaccines and the catchup for 2nd Vaccines on first visits which will be planned to complete by 15th December
7. School Sessions for the 2nd MMR vaccines (following on from the 1st administered in Autumn 2023) will be offered from January 2024 to February 2024 with an additional opportunity for catch up over the February half term if required.
8. Consider catch up sessions in October half term and December holiday if conversion % of consent to received vaccine is less than 90%
Delivery timeline and plan
1. Schedule of school visits (in line with MMR uptake data) to be shared with GM SIT and localities.
2. Plan the delivery with localities

## Slide 5: Data Recording and Sharing
Weekly/Monthly Spreadsheet return to CHIS to maintain imms records and update GP’s (review of a CSV file)
Monthly update to a Schedule 6 / spreadsheet format for the commissioning team overview
Vaccination status will be updated from the paper consents and the e-consent system within 3 working days onto systm1 / shared to GP (to be reviewed on best route for this)
CSV file for weekly MMR folder

## Slide 6: GMSIT next steps
Discuss and agree the proposed delivery model with SROs (26/7/23) and make any amendments before 28/7/23. Public Health and Intrahealth to agree financial model and contract.
Internal planning and scheduling from Intrahealth. To share the schedules with GM SIT and SROs (August). Intrahealth to link with SROs for support with engagement and promotion with schools.
CHIS and Intrahealth to work together re: data requirements. (August)
GM SIT to circulate comms to primary care.
GM SIT to share monthly progress reports with SROs. SROs to link directly with Intrahealth to discuss next steps, delivery and any queries following reports.